# Project Logical Framework

Digital Skills Training Center · $180K

# Impact (5 years)

Youth unemployment reduced from 34% to 22% in Cedar Bay.

# Outcome (2 years)

220 of 300 graduates employed in digital economy roles locally or remotely.

# Output (project end)

300 youth (18–29) complete 6-month certified training.

12 employer placement agreements signed before course start.

# Key activities

Q1: Facility setup + curriculum

Q2–Q3: Training cohorts 1 & 2

Q4: Job placement + evaluation

# Budget breakdown

Training delivery: $98,000 (54%)

Equipment: $42,000 (23%)

Personnel: $28,000 (16%)

M&E: $12,000 (7%)

Illustrative sample generated from a fictional demonstration municipality ("Cedar Bay"). Names, data, and content are for demonstration only.

Generated by MuniGrowth — munigrowth.com