# Heritage Tourism Infrastructure Upgrade

Mediterranean Regional Development Fund · May 2026

City of Cedar Bay · GRANT APPLICATION PROPOSAL · MG-CB-PR-2026-001 · 15 May 2026

# 00  Executive Summary

| Metric | Value |
| --- | --- |
| Total Budget | $420,000 |
| Funding Requested | $345,000 |
| Duration | 18 mo. |
| Youth Beneficiaries | 2,400 |

Cedar Bay requests $345,000 from the Mediterranean Regional Development Fund to upgrade heritage tourism infrastructure, extend the visitor season beyond four months, and create formal employment pathways for 2,400 youth currently without structured training or placement support.

The proposal aligns with RDF heritage tourism priorities, municipal LED Plan 2026–2030 Priority 2, and stakeholder consensus from 127 participants consulted in Q1 2026. Municipal co-financing of $75,000 (18%) is committed; co-benefits include coastal resilience and youth employment targets required to close the single eligibility gap identified in grant matching.

Recommended action: Submit within 23 days — RDF heritage tourism window closes 15 June 2026. Align narrative to coastal resilience and youth co-benefits to meet eligibility criteria.

# 01  Background & Needs Justification

## Municipal economic context

Cedar Bay (population 24,800) derives 42% of formal employment from heritage tourism, yet visitor volumes remain concentrated in a four-month peak season. Youth unemployment among ages 18–29 stands at 34% — 12 percentage points above the regional average. Infrastructure gaps include unpaved heritage access roads, limited year-round visitor facilities, and no integrated digital visitor experience.

## Evidence base

| Indicator | Cedar Bay | Regional avg. | Gap |
| --- | --- | --- | --- |
| Employment rate | 61% | 73% | -12 pp |
| Youth unemployment (18–29) | 34% | 22% | +12 pp |
| Tourism contribution | 42% | 28% | +14 pp |
| Heritage visitors (annual) | 50,000 | — | — |

Needs assessment (Q1 2026) ranked heritage tourism infrastructure as Priority 2 (urgency score 85/100) with an active RDF funding window. Stakeholder consultations identified seasonal income volatility and youth unemployment as the two highest-priority concerns requiring donor co-investment.

# 02  Objectives & Expected Results

## Project objective

Upgrade heritage tourism infrastructure to extend year-round visitor engagement, create 150 direct and indirect formal jobs, engage 2,400 youth in vendor and programming pathways, and reduce youth unemployment from 34% toward 28% within three years of project completion.

## Expected results

| Level | Statement | Indicator | Target |
| --- | --- | --- | --- |
| Impact | Sustained heritage-led prosperity | Youth unemployment rate | 28% by 2029 |
| Outcome | Youth engaged in heritage economy pathways | Youth programme beneficiaries | 2,400 |
| Outcome | Year-round tourism employment | Season extension (months) | 8+ months |
| Output | Upgraded visitor facilities | Sites operational | 3 sites by Q4 2027 |
| Output | Heritage access road paved | Road length completed | 2.4 km |

## Alignment with LED strategic goals

Priority 2 — Heritage Tourism Infrastructure (Projects 2, 4, 8 in Cedar Bay LED Plan 2026–2030).

Vision target: year-round tourism employment share above 55% by 2030.

Cross-cutting: minimum 40% women beneficiaries in vendor and programming roles.

# 03  Activities & Implementation Plan

## Work packages

| # | Activity | Duration | Responsible |
| --- | --- | --- | --- |
| 1 | Visitor centre refurbishment & interpretive signage | Q2–Q3 2026 | Tourism office |
| 2 | Heritage access road paving (2.4 km) with drainage | Q3–Q4 2026 | Public works |
| 3 | Digital heritage trail & AR visitor experience | Q4 2026–Q1 2027 | Economic dev. unit |
| 4 | Youth vendor spaces & seasonal programming | Q1–Q2 2027 | Stakeholder liaison |
| 5 | Mid-term review & donor reporting | Q3 2027 | M&E officer |

## Implementation timeline

| Activity | Q2'26 | Q3'26 | Q4'26 | Q1'27 | Q2'27 | Q3'27 |
| --- | --- | --- | --- | --- | --- | --- |
| Visitor centre refurbishment & interpretive signage | ◆ | ◆ | — | — | — | — |
| Heritage access road paving (2.4 km) with drainage | — | ◆ | ◆ | — | — | — |
| Digital heritage trail & AR visitor experience | — | — | ◆ | ◆ | — | — |
| Youth vendor spaces & seasonal programming | — | — | — | ◆ | ◆ | — |
| Mid-term review & donor reporting | — | — | — | — | — | ◆ |

Implementation note: Phased contractor milestones reduce construction delay risk. Municipal LED Steering Committee provides monthly oversight; quarterly reports submitted to RDF per grant agreement.

# 04  Budget Summary

| Category | Amount (USD) | Share | Source |
| --- | --- | --- | --- |
| Visitor centre refurbishment | $180,000 | 43% | RDF grant |
| Access road paving | $165,000 | 39% | RDF grant |
| Digital signage & AR trail | $75,000 | 18% | Municipal co-financing |
| Total | $420,000 | 100% |  |

| Funding line | Amount | Status |
| --- | --- | --- |
| Total project budget | $420,000 | Approved in LED plan |
| Secured (municipal allocation) | $75,000 | Committed FY2026 |
| Requested (RDF heritage window) | $345,000 | Pending submission |
| Funding gap if not awarded | $345,000 | — |

Co-financing: Municipal co-financing of $75,000 (18%) covers digital heritage components and is committed in the FY2026 capital budget. RDF grant covers civil works and visitor facilities.

# 05  Logical Framework

| Level | Description | Indicator | Verification | Assumptions |
| --- | --- | --- | --- | --- |
| IMPACT | Youth unemployment reduced; heritage assets generate year-round prosperity | Youth unemployment rate | Labour survey | Macroeconomic stability; continued protection of heritage assets |
| OUTCOME | Year-round tourism employment; 150 jobs; 2,400 youth beneficiaries | Employment / season length / youth reach | Employer registry; tourism office; programme records | Tourism demand holds; youth recruitment targets met through schools and outreach |
| OUTPUT | 3 heritage sites upgraded; 2.4 km access road complete | Sites operational; km paved | Site inspections; progress reports | Contractors available; weather windows respected |
| ACTIVITIES | Construction, programming, digital trail launch, youth vendor rollout | Milestones delivered | Contractor & municipal records | RDF grant disbursed on schedule; municipal co-financing released |

# 06  Monitoring & Evaluation

The M&E framework tracks progress against logical-framework indicators using standardised data collection tools and quarterly reporting to municipal council and RDF.

| Indicator | Baseline | Target | Frequency | Responsible |
| --- | --- | --- | --- | --- |
| Youth unemployment (18–29) | 34% | 28% | Semi-annual | M&E Unit |
| Youth programme beneficiaries | 0 | 2,400 | Quarterly | Stakeholder liaison |
| Heritage visitors (annual) | 50,000 | 65,000 | Quarterly | Tourism office |
| Year-round employment share | 45% | 55% | Annual | Economic dev. unit |
| Road completion (km) | 0 | 2.4 | Monthly | Public works |
| Women vendor placements | 0 | 24 | Quarterly | Stakeholder liaison |

## Evaluation milestones

Inception report — within 30 days of grant signature.

Mid-term review — Month 9 (construction progress, beneficiary outreach).

Final evaluation — Month 18 (impact indicators vs. baseline).

# 07  Organisation & Contact

| Role | Office | Contact |
| --- | --- | --- |
| Project Director | Mayor's Office | mayor@cedarbay.demo |
| Technical Lead | Economic Development Unit | led@cedarbay.demo |
| Financial Controller | Finance Department | finance@cedarbay.demo |
| M&E Officer | Planning Department | me@cedarbay.demo |
| Grant Focal Point | Mayor's Office | grants@cedarbay.demo |

## Implementing arrangement

The Municipal LED Steering Committee (Mayor, department heads, private sector and youth representatives) provides monthly oversight. Day-to-day coordination sits with the Economic Development Unit. All procurement follows municipal transparency standards and RDF grant requirements.

| Submission reference | Value |
| --- | --- |
| Applicant | City of Cedar Bay |
| Programme | Mediterranean Regional Development Fund — Heritage Tourism |
| Document ID | MG-CB-PR-2026-001 |
| Submission deadline | 15 June 2026 (23 days) |
| Prepared using | MuniGrowth LED Planning Platform |

Illustrative sample from fictional demonstration municipality (Cedar Bay). Names, data, and content are for demonstration only.

Generated by MuniGrowth — munigrowth.com